## Sheet1
Sr. No. | Issue/Task | Type of issue | Remark | Status | Priority
1 | E-Mail Subject : ज़ी लैब स्कीम अप्रूवल के संदर्भ में | Issue |  | Open | Very High
| In this case effective credit limit is 1,75,000/-, Credit Limit already consumed Rs. 2,21,125. User book a new ad of 12,650/- for 26/08/2020 but system did not stop this ad for publication. |  |  |  |  | vishal
2 | E-Mail Subject : Retainer RO | Issue / Task |  | Partially Done | Very High | Sunday
Many changes already done by Mr. Saurabh Sharma in test database.
It is pending for updating on Production.
3 | E-Mail Subject : Deal Management : Pending Issues / Tasks | Issue / Task | Total 4 high priority tasks are mentioned in this mail. | Open | High | bhanu
Consolidated task list related to deal management. These tasks are pending since long, please take it up on priority.
4 | E-Mail Subject : Need to add new reason for inactivation of agency | Task |  | Open | High
| We need to get ‘INACTIVE DUE TO AGREEMENT NOT DONE’ reason updated in attached some inactive agencies. |  |  |  |  | done
5 | 0025985: Issue in material assigning-Vinay | Issue |  | Open | High
| If any two insertions book in same date and materials are different in every edition, it is very difficult to assign material.Please check this issue and provide the solution on priority. We have raised the issue in the beginning but we did not get any solution till the date. please help. |  |  |  |  | under-testing by au
6 | E-Mail Subject : Changes in Bulk Booking System | Task |  | Open | Medium
| We need to provide an option to attach RO and Other Document from Bulk Booking form. This would similar to the existing option of Booking module. |  |  |  |  | vishal
7 | E-Mail Subject : Wrong City Showing with client name | Task |  | Open | Medium | billto client | city not print
| In case of coupon, need not to display city of client (mentioned in master). |  |  |  |  | sub-cat-coupo (shalu)
8 | E-Mail Subject : Showing wrong GST Amount in Proforma Invoices | Issue |  | Open | Medium
| It is showing wrong GST amount (just double), however total bill amount is correct. |  |  |  |  | shalu
This issue comes when booking has 2 insertions.
9 | E-Mail Subject: Without client name Booking Save/Meerut | Issue |  | Open | Medium
| In the coupon booking cases,Some cases without client name has been save. |  |  |  |  | vishal
DME0202000006356,DME0202000006357, DME0202000006358, DME0202000006359, DME0202000006360
10 | E-Mail Subject: matrimonial advt.. | Issue |  | Open | Medium | bhanu
booked below booking with bold & frame but after flow advt not showing in bold matter.
Booking no. CNA0202000001737 issue already duscuused with Bhanu Ji.
11 | E-Mail Subject :Launching ......... COUPON MANAGEMENT system in CIO | Task |  | Open | Medium | shalu
System does not validate the coupon Size and Rate/Amount. AND We could not re-issue the coupons once we return these coupons. AND Need to add two more 'COMMON RETURN TYPE', one 'Transfer' and second Re-issued.
12 | E-Mail Subject : Coupon Detail Report : Need some changes | Task |  | Open | Medium
| As discussed, please find below issue of Detail Report. |  |  |  |  | vishal
1. Unit filter is not working.
2. Booklet Type is not working. We need multi selection option in Booklet Type filter.
3. Name of unit is not showing in the report. Add this column also.
13 | E-Mail Subject : Mapping of client with agency | Task |  | Open | Low
User should be able to book ads of related clients with following In House agencies.
14 | Changes required during dummy release | Task |  | Open | Very High
15 | E-VTS | Task |  | Open | Very High
16 | Agency Portal | Task |  | Open | Very High | shalu
17 | Place of Supply on Advertisement Invoice | Issue |  | Open | Very High | done
18 | IRPD Bill print required on separate format. | Task |  | Open | Very High | done
19 | Cheque Bounce Marking & Outstanding Report | Task |  | Open | Very High
20 | Commission Calculation process | Task |  | Open | Very High
21 | Agency Receipt Register report | Issue |  | Open | Very High
22 | Discount Approval Status required in Unbilled Report | Task |  | Open | Very High | shalu
23 | Discount Approval | Task |  | Open | Very High
24 | In-AU Report-Agency Bill Wise Status Report-(Add-MRV Ref No) | Issue |  | Open | Medium
25 | Invoice, CN & DN should save in PDF | Task |  | Open | Medium
26 | Invoice upto Filter Required in Unadjusted Receipts Register | Issue |  | Open | Medium
27 | Coupon count and coupon price should show in a separate column so that user can check and verify billing amount with coupon count. | Task |  | Open | Medium
28 | Coupon number should display on front so that user can also check and verify the coupon number if required, for this we should show a button of coupon if user tick on that button then all the coupon number displayed. | Task |  | Open | Medium
29 | Header and first 3 column (S. No. Status & Booking) should be freeze so that it will not move while going down or right. | Task |  | Open | High
30 | Attachment column should be wrap text if more than one attachment in booking then column width should not increase, Row height should be increased and attachment should show in multiple lines. | Task |  | Open | Very High
31 | Agency Type should also be display on the RATE AUDIT form. | Task |  | Open | Very High
32 | In case we are doing bulk booking, we should generate any reference number or any other option which can be selected at the time of Rate Audit in searching criteria so that all the bulk bookings of single RO could be tracked at the time of Rate Audit. | Task |  | Open | Medium
33 | System should not allow bulk booking in XYZ Agencies (Not to Bill Agencies) while using bulk booking option, a message should show that you can not book the advert in XYZ Agency by using the Bulk Booking option. | Task |  | Open | Medium